## Report
[Project Title]
Earned Value Analysis Report
| Prepared By: | Brendan Dwyer
| Date: | 2024-04-30
[42]
| For Period: | 4/18/24-4/30/24
Summary:
This sheet shows the cost of time spent on each task for the development of our OSINT application
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Creating Concept | 1500 | 1200
1.2 | Finding API's | 550 | 250 | 200 | 100
1.3 | Developing Processes | 1400 |  | 200 | 200 | 400 | 200 | 400
1.4 | Creating Dashboard | 1400 |  |  | 400 | 200 | 600 | 200
1.5 | Developing Complete App | 2400 |  |  |  | 200 | 200 | 600 | 400 | 400 | 400 | 200
1.6 | Reports (Proj manage, Risk, etc) | 6100 |  | 400 | 400 | 600 | 1500 | 400 | 600 | 400 | 600 | 400 | 400 | 400
0
0
0
0
0
0
Insert new rows above this one
| Total Budgeted Cost | 13350 | 1450 | 800 | 1100 | 1400 | 2500 | 1600 | 1000 | 800 | 1000 | 600 | 400 | 400
|  | Cumulative Planned Value (PV) | 1450 | 2250 | 3350 | 4750 | 7250 | 8850 | 9850 | 10650 | 11650 | 12250 | 12650 | 13050
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 1450 | 2250 | 3350 | 4750 | 7250 | 8850 | 9850 | 10650 | 11650 | 12050 | 12250 | 12050
|  | Cumulative Earned Value (EV) | 1201 | 1348 | 1759 | 1424 | 1275 | 1665 | 1887 | 1237 | 1339 | 1216 | 2233 | 1684
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -249 | -902 | -1591 | -3326 | -5975 | -7185 | -7963 | -9413 | -10311 | -10834 | -10017 | -10366
|  | Schedule Variance (SV = EV - PV) | -249 | -902 | -1591 | -3326 | -5975 | -7185 | -7963 | -9413 | -10311 | -11034 | -10417 | -11366
|  | Cost Performance Index (CPI = EV/AC) | 0.82828 | 0.59911 | 0.52507 | 0.29979 | 0.17586 | 0.18814 | 0.19157 | 0.11615 | 0.11494 | 0.10091 | 0.18229 | 0.13975
|  | Schedule Performance Index (SPI = EV/PV) | 0.82828 | 0.59911 | 0.52507 | 0.29979 | 0.17586 | 0.18814 | 0.19157 | 0.11615 | 0.11494 | 0.099265 | 0.17652 | 0.12904
|  | Estimated Cost at Completion (EAC) | 16117.8185 | 22283.0119 | 25424.9574 | 44531.25 | 75911.7647 | 70959.4595 | 69686.0095 | 114937.3484 | 116151.9791 | 132292.352 | 73236.6771 | 95527.019
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Creating Concept | 1500
1.2 | Finding API's | 550
1.3 | Developing Processes | 1400
1.4 | Creating Dashboard | 1400
1.5 | Developing Complete App | 2400
1.6 | Reports (Proj manage, Risk, etc) | 6100
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Creating Concept
1.2 | Finding API's
1.3 | Developing Processes
1.4 | Creating Dashboard
1.5 | Developing Complete App
1.6 | Reports (Proj manage, Risk, etc)
- | -
- | -
- | -
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0